## 14 APR 2015
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks | Assigned Date | Completed Date | Status | Remarks
1 | Overall Job | Record View Feature | Missing | enable view option without download.
2 | menu (side bar) | - |  | hanging
3 | Instrument Costing | contract discount |  | correct the miscalculate value
4 | Customer Tag | address | bug | address missing
5 | quotation | unit discount |  | limit need to be enable
6 | All job | refresh button |  | for latest customer info
7 | Customer Tag | Labprocess & Client PO Approve |  | something wrong. Error there.
8 | Delivery order (Partial) & c and d | address |  | it should be delivery address.
9 | c and d report | format |  | correct the format for emty pages.
10 | quotation and invoice | gst |  | something wrong. Error there.
11 | Invoice |  |  | correct missing things as discussed.
12 | PO & PI |  |  | FOLLOW INVOICE FORMATE
13
14
15
16
17
| JOBMONITORING |  |  | COMPLTED ITEMS IN SEPARATE TAB.
29
30
31
32
33
34
35
36
37

## 10 APR 2015
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks | Assigned Date | Completed Date | Status | Remarks
1 | JOB | JOB TRANSACTION | MISSING | JOB TRANSACTION MISSING FROM MENU
2 | INTRUMENT | RANGE | CORRECTION | IF END VALUE NOT ENTERED, THE RETUR FORMAT SHOULD "(100)/BAR
3 | INTRUMENT | PROCEDURE | CORRECTION | CHECK DOUPLICATION.
4 | CUSTOMER | COSTING | FEEDBACK | RESET COST,DISCOUNT,PRICE FILED AFTER ADD.
5 | CUSTOMER | COSTING | CORRECTION | PRICE NOT CALCULATING CORRECT WHEN UPDATE CONTRACT-DISCOUNT.
6 | OVERALL | SEARCH-HEADER (UNIT) | CORRECTION | PLEASE CHECK BCOZ SOME COLOUM NOT WORKING WHEN SEARCH
7 | OVERALL | JOB | CORRECTION | DISCOUNT LIMIT SHOULD BE LESSER THAN ASSIGNED %VALUE. OVERALL DISCOUNT SHOULD APPLY FOR ALL ITEMS (DISCOUNT) AND CAN OVERWRITE IF REQUIRED.
8 | LABPROCESS & JOB MONITORING | COUNT | CORRECTION | COUNT NEED TO CORRECT FOR PROCESSING ITEMS.
9 | DELIVERY ORDER & JOB MONITORING | COUNT & STATUS | CORRECTION | MISMATCHING
10 | C AND D | READY TO DELIVER | MISSING | MISSING ITEMS FOR PARTIAL DO JOB (WHEN ADD NEW )
11 | JOB | INVOICE | CORRECTION | PARTIAL DO - INVOICE SHOULD NOT GENERATE BEFORE COMPLETE ALL ITEMS.
12 | OVERALL | REPORT | CORRECTION | 1.) ADDRESS, AND REG.NO. (HEADER) AND 2.) COMPANY NAME (FOOTER) MUST AUTO FROM BRANCH TABLE. 3.) REMARKS DOEST DIPLAY IT SHOLD BE DISPLAY FROM SO REMARKS. 4.) CURRENCY WRONGLY DIPLAY.PLEASE CHECK AND CORRECT. 5.) DO REPORT FORMAT- (LINE) NEED TO CORRECT. 6)INVOICE FORMAT MUST BE NEAT.
13 | Job | Quotation | CORRECTION | 1.) Feedback- In report, the value (CPO-15-xxxxxx) replace with "-" until put Original PO# Number. 2.) If value entered in this field, it should be display in remarks field automatically (DO & Invoice) and if contain any of these (FAULTY, NO CAPABILITY, RETURN WITHOUT CAL, OUT OF TOLERANCE, AND JOB CANCELLED.) it should zero-price in invoice automatically. This was discussed earlier very clearly.
14 | JOB | INVOICE | CORRECTION | ADDRESS NOT CORRECT,PLEASE CHK.
15 | JOB | SUB-CON | CORRECTION | PHONE NO.& "INSTR FOR" FIELDS MISSING WHEN APPROVAL.
16 | JOB | PO | CORRECTION | PRICE CAN NOT EDIT
17 | JOB | PO-PRINT | CORRECTION | GOES TO ERROR PAGE.
| JOB | PO,PR-PO REPORT | CORRECTION | PR & PR-PO REPORT FORMAT NEED TO BE PROPER. 2.) PR NO. MISSING IN REPORT 3.) PO & PR IS MISSING
| JOBMONITORING |  |  | COMPLTED ITEMS IN SEPARATE TAB.
29
30
31
32
33
34
35
36
37

## 02 APR 2015
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks | Assigned Date | Completed Date | Status | Remarks
1 | User & Roles | Instr. Costing | Missing | Instrument Costing (View & Edit) - Assigned already to user but No Icon to do.
2 | User & Roles | Approval (Instr.Cost) | Missing | Approval Rights missing for Instr.Costing in Approval Dashboard. But View & Edit implemented Already.
3 | Dashboard | Total Task Qty | Bug | Total Task Quantity is wrong - To Approval. It should display what modules assigned and total quantity of pending to approve.
4 | User | Service Type | Bug | Error Screen Appear when edit record. It will hang whole software if this error arised.
5 | Instrument | Procedure | Bug | Compulsory field cannot allow null value.
6 | OverAll | Compulsory field | Bug | Please check and rectify for compulsory fields. It should be a value instead of null value.
7 | Instrument | Procedure | Bug | When approve the dept value changed as "Electrical" but still display Misc. dept.
7.1 | Job | Quotation | feedback | ADD/EDIT INSTRUMENT OPTION AFTER SAVE. AS EXISTING DELTA SOFT | STILL NO OPTION TO ADD INSTR. BUT EDIT/DELETE OPTION DONE. | Last time reported.
8 | Job | Quotation | Bug | 1.) Feedback- In report, the value (CPO-15-xxxxxx) replace with "-" until put Original PO# Number. 2.) GST value is wrong because it should be calculated after Discount & additional charge 3.) Discount value should not round up into full number.It should be round up 2 decimal as screenshot 4.)BSQ-15-000009 How allowed 50% discount (Note: Max 40%,User can put 10%).
9 | Job | Quotation | Bug | Please check quotation BQS-15-000009 & BSQ-15-000009. Missing additional charge in report but inputed in both quote. Additional charge value should be before GST. That meant it should be added with subtotal and calculate gst. Its not necessary to apply discount if enter overall discount.
10 | Job | Quotation | feedback | BQS-15-000009 - Please follow attached sample report (sample form with unit discount.pdf) if unit discount applied. As existing BSDelta. Otherwise client cannot identify where discount applied.
11 | Job | Salesorder | Bug | Report alignment issue. | NOT SETTLED YET. | Last time reported.
12 | Job | Salesorder | Bug | Before save sales order removed 3 items and saved with 2 item partial sales order. But it shows deleted items in approval dashboard. This error is happened many times earlier. Please correct it properly for all jobs. Its very big logical error. | NOT SETTLED YET. | Last time reported.
13 | Overall | Report | feedback | As informed,Only display compulsory fields and hide other fields if no data.(ect.,TagNo.,Location) | NOT SETTLED YET. | Last time reported.
14 | Job | Salesorder | Bug | In report, range value is missing and null for some instruments. How come empty value in range for compulsory field.
15 | OverAll | Report | Missing | Compulsory Fields in Report: (ITEM ¦ QTY ¦ INSTRUMENT ¦ BRAND ¦ MODEL ¦ RANGE ¦SERIAL NO. ¦ REMARKS ) and (TOTAL PRICE ¦ UNIT DISCOUNT (if applied)) Optional Fields in report:(ect.,TagNo.,Location) | Informed many times.
16 | Lab process | Reson of delay | Missing | If value entered in this field, it should be display in remarks field automatically (DO & Invoice) and if contain any of these (FAULTY, NO CAPABILITY, RETURN WITHOUT CAL, OUT OF TOLERANCE, AND JOB CANCELLED.) it should zero-price in invoice automatically. This was discussed earlier very clearly.
17 | c and d | edit | Bug | After added one date. When do edit particular date record to add collection, the ADD button disabled.
19 | c and d | Compulsory field | Bug | please verify compulsory field because without "purpose of" filed still allow to save.
20 | c and d | report | Bug | no data in report. Already happened this same issue. Its intermittent. And must display "assigned to" filed in report.
21 | Invoice | report | Bug | Follow issue no. 8,9,10 & 16.
22 | Subcon-Do | report | Bug | Display wrong subcontractor name.
23 | purchase order | report | Bug | it goes to error screen when click report button.
24 | PR & PO | Compulsory field | Bug | Withou contact "Attn" field, It allow to save. Please correct it.
25 | Job | PR | Missing | PR report is missing.Please do PR report. | NOT SETTLED YET. | Last time reported.
26 | performa invoice | report | Bug | Follow issue no. 8,9,10 & 16.
27
28
29
30
31
32
33
34
35
36
37

## 30 MAR 2015
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks | Assigned Date | Completed Date | Status | Remarks
1 | Job | Quotation | Bug | There is no range value & brand. Its intermittent.
2 | Job | Quotation | Bug | Range & Brand are compulsory field but System allow to save withou range/brand.
3 | Overall | Grid View - Sort | feedback | Sort by latest records first. As existing bsdelta.
4 | Overall | Report | feedback | As informed,Only display compulsory fields and hide other fields if no data.
5 | Job | Quotation | Bug | Discount & Special Charge are not display in report. But inputed in quote form.
6 | Job | Quotation | Bug | Already Informed. Compulsory fields cannot allow null.
7 | Job | Quotation | Bug | Already Informed. Unit Price & Total Price cannot be same if discount applied. In Report, Discount not display too.
7.1 | Overall | Date Format | feedback | Still not follow standard format. It should be "DD-MMM-YYYY". As existing Bsdelta
8 | Job | Salesorder | Bug | Report alignment issue.
9 | Job | C and D | Bug | After tick first 2 items "R", it doesn’t reflect in c&d ready to deliver list.
10 | job | Job Monitoring | Bug | Status Wrongly display.
11 | Job | C and D | Bug | Prompt wrong error message after enter "assignto" value and save.
12 | Job | PR | Missing | PR report is missing.Please do PR report.
13 | Job | PR | Missing | Remarks doesn’t appear in grid but selected.
14 | Job | PR-PO | Bug | 1. No Price but saved. It allow null value in PR. 2. PR-PO Price must editable like quote & invoice.
15 | Job | Tracking System | Missing | Remarks and Response person - editable. As existing Bsdelta.
16 | Job | Tracking System | Missing | Filter - Conditional fields must include as grid fields.
17 | Job | Invoice | Bug | Report Discount doesn’t reflect and total vaue is wrong.
19 | Job | Invoice | Missing | Already Informed.Please remove too much of lines and follow as existing format.
20
21 | Job | Quotation | feedback | ADD/EDIT INSTRUMENT OPTION AFTER SAVE. AS EXISTING DELTA SOFT
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37

## 26 MAR 2015
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks | Assigned Date | Completed Date | Status | Remarks
1 | USERS | C&D settings | bug | Even if the "C& D settings" is not assigned to the user role, it still appear in the menu bar.
2 | INSTRUMENT, BRAND | SEARCH | bug | Alpha search not working, numeric search working
3 | INSTRUMENT | PROCEDURE | BUG | error, mySQL
4 | BRAND, RANGE, UNIT, LIST OF INSTRUMENTS | SEARCH, STATUS | bug | Unable to search STATUS inactive or active, alpha search not working
5 | INSTRUMENT | unit | bug | duplicating
6 | DASHBOARD | CUSTOMER APPROVAL | BUG | Approval Dashboard still shows customer for approval, even after approving (intermittent)
7 | CUSTOMER | INSTRUMENT PRICING | BUG | RANGE IS LOCKED, UNABLE TO TYPE, ONLY DROP DOWN. (NOT AUTOCOMPLETE SEARCH)
7.1 | QUOTATION | DISCOUNT | bug | NOT REFLECTED
8 | SALES ORDER | DATE | BUG | format
9 | SALES ORDER | STEP 3 INSTRUMENT | BUG | Sales order extract from Quotation, no option to remove items, say partial.-[ double check only)
10 | OVERALL | DATE | FEEDBACK | MUST BE : (DD-MMM-YYYY) EXAMPLE: 26-MAR-2015
11 | OVERALL | REPORTS | FEEDBACK | PLEASE FOLLOW OUR FORMAT ON THE COLUMNS TO APPEAR. IE.
12 | LAB PROCESSING | REASON OF DELAY | FEEDBACK | Must follow same as our current system. To fix exact remarks like ; FAULTY, NO CAPABILITY, RETURN WITHOUT CAL, OUT OF TOLERANCE, AND JOB CANCELLED. These words should reflect in our Delivery Order under Remarks column, and should automatically convert the price to Zero. (0.00) in our quotation and invoice.
13 | JOB MONITORING | DOC | BUG | The DOC is ticked even if P and C are not ticked. Logically, DOC should only be ticked if Delivery Order is done.
14 | C&D | Collection | missing | Phone number for the contact person (attn to) should reflect the phone number of the customer.
15 | C&D | C&D Report | missing | No data found
16 | C&D | Approval Dashboard | missing | Why is there an approval dashboard to approve if we cannnot even see what to approve. Its not logical, clicking approve without knowing what to approve.
17 | JOB MONITORING | Done Status | bug | Job monitoring already has ticked D, even if C&D "Job Done " is still untick.
19 | Delivery Order (Partial) | Dashboard | bug | After approving Client PO, the process did not go to the Delivery Dashboard.
20 | Delivery Order (Full) | status | missing | After ticking P&C for the items to complete the order, there is no delivery order created. However there is 1 item in the invoice dashboard approve. Invoice is complete, but there is only 1 delivery order
21 | LAB PROCESSING | STATUs | FEEDBACK | P SHOULD NOT BE ABLE TO UNTICK IF C IS ALREADY TICK. OTHERWISE, MUST UNTICK C FIRST TO UNTICK P
22 | INVOICE | REFERENCE | BUG | REMOVE DUMMY PO, MUST ONLY SHOW ACTUAL PO NUMBER
23 | PO | PRICE | BUG | THE PRICE IS NOW EDITABLE, BUT IT DOESN’T REFLECT SAME AMOUNT IN THE TOTAL
24 | CUSTOMER | CONTACT INFO | BUG | mail id is a must (validate). Remove asterisk on Phone
25 | PR | FIELDS | BUG | CUSTOMER NAME IS NOT VALIDATE AND CREATED, BUT THE SYSTEM ACCEPTED AND SAVED. WITHOUT ENTERING VAUES IN THE FIELDS, IT WAS SAVED.
26 | PR | Accounts Service field |  | Must be editable.
27 | PR PO | Approval | bug | Dashboard has PR PO, but has not approved button
28
29
30
31
32
33
34
35
36
37

## 13 MAR 15
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks | Assigned Date | Completed Date | Status | Remarks
1 | Users | Roles | bugs | After assigning dashboard(complete), unable to view Graph and Overall Stats-Numbers.
2 | Users | Roles | missing | C&D Settings permission missing. This is a critical option as not all users should be able to access/edit or delete.
3 | Overall | Range search | limited option | Range search should be same as the existing system. Ie, range 0~360, if you enter 360, all ranges that contains 360 must populate...
4 | Customer | Customer Tag | missing | Customer TAG doesnt identify the customer. It appears as duplicate in the grid although TAG was already assigned.
5 | Overall | Grid | bugs | Please allow grid to be expanded in order to view complete details in the cell
6 | Instruments | Instrument | mismatch | We added instrument name "Digital Temperature Gauge", on approval it displays as "digital temperature" only. Another issue, it combined with other instruments which we did not add in (shown in brand and range)
7 | Customer | Instrument Costing | mismatch | After clicking approve button in dashboard, no info in the details page.
8 | Customer | Customer Costing Approval | redundant button | Remove update button, retain approve button.
9 | Jobs | Quotation | bug | Discounting. The unit price reflected should be the actual price. Display discount in another field and then display Total (actual price less discount)
10 | Overall | Grid View | not effective | all the columns/fields are forced in one page, you can use scroll bars in order to display the details properly as our existing system
11 | Overall | Grid View | not effective | Please refer to our existing system, they are neatly done with appropriate font size , must use left alignment for all except for titles, header and footer colors must be darker for emphasis.
12 | Quotaton | Label | spell error | CALL LOCATION should be "Cal Location"
13 | Quotation | Cal Location | bugs | Cal location must be compulsary. Another thing, all compulsary fields should be identified with red asterisk(*) same as our existing system.
14 | Sales Order | Step 3 | bugs | Please add in the edit and delete buttons to update
15 | Lab Process | Dashboard | bugs | After approving the partial Delivery Order, still able to untick C or P. Please ensure that the item with delivery order issued should not be editable (grayed out). Another thing, in the lab process dashboard, the status counting is wrong.
16 | Job Monitoring | Dashboard | bugs | The "DOC" and "S" status are missing. Please complete
17 | C&D | Ready to Delivery items | missing | Please ensure that ready to deliver items should appear in all dates.
18 | C&D | Save | missing | After saving, it doesnt prompt if it was successfully saved. Another thing after saving, it should go back to C&D dashboard.
19 | C&D | Shipped and Delivered tick boxes | bugs | as informed earlier its should not be "delivered".. It should be "do0ne". Another thing the Done (delivered) tick box is not visible (missing)
20 | Approval Dashboard | C&D | feedback | How does the C&D Approval works? We realized that the Collection flow can proceed even without approving it.
21 | Related to issue #19 Job monitoring | Status | bugs | "Done" (delivered) is automatically checked even without the tick box update in the C&D. Logic issue
22 | JOBS | Subcontract DO | bug | Labels in now for Subcontractor but please but "Subcontractor" not "Subcontract Name"; For "Customer Address" Just put Address.
23 | JOBS | Purchase Order | bug | Unit Price should be editable because Subcontract price it is not necessarily same price as our quoted price to the customer. Labels not for Customer but for Subcontractor instead. Please update Above is now ok,but intermittent, sometimes it doesnt work, sometimes it works. Please verify
24 | JOBS | Purchase Requisition | bug | Labels not for the customer but for Supplier instead. Please update including the address, For "Customer Address" Just put Address.
25 | JOBS | Purchase Requisition | bug | Added items but doesnt reflect them when about to approve. (supervisor approval)
26 | JOBS | Purchase Requisition Report | bug | There is no button to open report. Report is missing
27 | JOBS | PR_Purchase Order | bug | There is no price related fields.
28 | JOBS | Invoice | bug | Please check alignment and please do as the current system.
29 | Invoice | Invoice Report | layout | Some fields overlapped, fonts and spacing are not coordinated, footer too high. As mentioned earlier, please avoid too many lines and follow same as existing reports.
30 | Quotation | Quotation Report | layout | Please check right margin.
31 | Overall | REPORTS | layout | Please follow the font and font size of our existing reports, specially the Job Title and Job Number. Standardize spacing, footer, fonts sizes alignments, margins in all reports
32 | Sales Order | Sales Order Report | layout | Footer is too big, Special requirement not properly aligned.
33 | Delivery Order | Delivery Order Report | ERROR | No Report
34 | Purchase Order | PO Report | layout | Footer is too big, Special requirement not properly aligned.
35 | Subcontract DO | Subcontract DO Report | layout | Footer is too big, Special requirement not properly aligned.
36 | JOB | Job Transaction | Missing | Job Transaction is missing.
37 | JOBS | Traacking System | Incomplete | Please follow format of existing system -1.) split into 2 tabs (incomplete and completed. 2.) Under incomplete, it should have option to update completed check box, remarks text, responsible person selection. 3.) Kindly include individual field search. 4. Also include the status counting, like processing, Pending, Awaiting and Completed

## 06 MAR 15
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks - 13 -3 updates | Assigned Date | Completed Date | Status | Remarks
1 | Load Performance | overall | improve | Brand (2391 data) 25.5 secs loading time; Range (5960 data) 1min 19secs. [Note that our existing system loads Brand at 2.5 secs (2404 data), Range, 1 sec (5987 data)] Please improve the performance at least same as the existing. | ok
2 | USERS | Department field | bug | It still shows deleted items. | ok
3 | ROLES | User Roles | mismatch | The approval dashboard roles has too many permissions, like add, edit, delete view. Please explain. Our existing system approval dashboard permission is only VIEW to approve. | ok
4 | ROLES | Datalogs | missing permission | Datalog has no permission, please create. Not all roles should be able to access datalogs. | ok
5 | ROLES | Jobs | - | Please explain what is Resistance BS20141 and Form Datas | removed- ok
6 | USERS & ROLES | Permissions | bug | Roles assigned doesnt match permissions. Its a very critical area due to information confidentiality. Please ensure that roles & permissions tally and correct. | ok except for missing dashboard
7 | CUSTOMER | Approval | bug | Upon approval, the updated data are missing, example address and contact details. This problem already pointed out earlier. | ok
8 | CUSTOMER | Contacts | bug | The grid is not properly aligned. | ok
9 | INSTRUMENT | Procedure No | bug | Deleted departments still shows in the selection. Please correct. | ok
10 | INSTRUMENT | Instruments | bug | Deleted departments still shows in the selection. Please correct. | ok
11 | CUSTOMER | Customer Costing Approval | feedback | Remove update button, retain approve button. | pending
12 | JOBS | Quotation | bug | Discounting. The unit price reflected should be the actual price. Display discount in another field and then display Total (actual price less discount) | pending
13 | JOBS | Quotation Report | feedback | Please put discount in line with the subttotal | 1
14 | JOBS | Quotation | bug | Added Item disappears after saving.
15 | JOBS | Sales Order | bug | Data missing after saving. (ie brand or range). System is not stable
16 | JOBS | Sales Order - pending | bug | Pending items went missing.
17 | JOBS | Sales Order | feedback | Our Reference is missing. (it should be the quotation which reference the Sales order sames as the existing system)
18 | JOBS | Sales Order | bug | When preparing partial sales order from quotation, the items were missing after saving. And also, the partial items are also not searchable under pending. (BQS-05-004004/ SaLES Order BSO-05-004006
19 | JOBS | Sales Order | bug | Approval of Sales Order is not stable, sometimes it allows to approve, sometimes it doesnt respond. Another thing, it doesnt show in the Approval Dashboard.
20 | JOBS | Delivery Order | feedback | The instrument grid is not properly aligned.
21 | JOBS | Delivery Order | bug | Partial delivery order, but Delivery order report shows all the items in the sales order. After completing the other batch, P&C ticked in Lab Process, the Delivery Order Report generated is the same as the full sales order. Another thing, Remarks on Delivery Order report should be placed on the last column.
22 | JOBS | Client PO | bug | Able to update Manual PO, but it doesnt show approve button so unable to proceed to invoicing.
23 | JOBS | Tracking System | bug | The instrument grid is not properly aligned. Missing Customer name for BSO-05-004003 and BSO-05-004002
24 | JOBS | Job Monitoring | feedback | The instrument grid is not properly aligned.
25 | JOBS | C&D | bug | Adding collection, customer phone number doesnt appear. Must automatically come up
26 | JOBS | C&D Report | bug | Segregate Page for each Assigned to (Person in charge), not only the table.
27 | JOBS | Subcontract Report | feedback | Footer not properly aligned. Remarks on Subcontract DO should be placed on the last column.
28 | JOBS | Purchase Order | bug | Unit Price should be editable because Subcontract price it is not necessarily same price as our quoted price to the customer. Labels not for Customer but for Subcontractor instead. Please update
29 | JOBS | Purchase Order Report | feedback | *BPO number is not in the box. *Footer not aligned. *Remarks should be on the last column. *Contact Details must be the Subcontractor's details not Customer details.
30 | JOBS | Purchase Requisition | bug | Labels not for the customer but for Subcontractor instead. Please update
31 | JOBS | Purchase Requisition Report | bug | There is no button to open report. Report is missing

## 23 FEB 15
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks | Assigned Date | Completed Date | Status | Remarks
1 | Admin | Dashboard-Costing Approval | Feedback | After approval,Need remove from list or highlight as approved bcoz user get confuse approved or not.
2 | Job | Datalog | Missing | Gridview not user friendly.Plz follow our existing bs enterprise
3 | Job | Tracking system | Missing | Gridview not user friendly.Plz follow our existing bs enterprise
4 | Job | PO | Error | Couldn’t Save. It goes to error page.
5 | Job | PI | Missing | Report does not completed with new format. Still old one there.
6 | Job | SubconDO | Missing | Report does not completed with new format. Still old one there.
7 | Job | PR-PO | Error | After saved there is missing instruments details in approval dashbord and report too.
8
9
10
11
12

## 05 FEB 15
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks | Assigned Date | Completed Date | Status | Remarks
1 | Admin | User-Brand | Feedback | For brand's "Description" field not mandatory.
2 | Customer | Contact | Missing | In customer form - "email" field must mandatory.
3 | Admin | Instruments-Unit | Feedback | For unit's "Description" field not mandatory.
4 | Customer | Prise | Feedback | Not user friendly - Approval must be open and option to edit or verify and save aprproval.
5 | Overall | Active-defualt | Feedback | Active-defualt
6 | Customer | Customer-Address | Missing | When update - the address rich field doest proper
7 | Job | Lab Process | Missing | Label For Instrument status (Follow as job monitoring)
8 | Job | Client PO Approval | Missing | Dashboard-Approval-Partial DO- For Client PO Approval
9 | Job | CandD | Bug | Partial Delivery item not goes to c and d.Please rectify.( Its moving only at the time of complete all items)
10 | Job | PR | Missing | Title (Multiple Selection)
11 | Job | PR-PO | Bug | Couldn’t Approve by manager
12 | Job | PO | Bug

## 22 JAN 15
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Error Remarks | Assigned Date | Completed Date | Status | Remarks
1 | Customer | Sales Person, Refered by, Priority, Payment Terms, Location, Industry | Missing in view list | AFTER ADD IN AND DELETE, UNABLE TO ADD IN AGAIN. WILL INFORM ALREADY EXISTS BUT DIDN’T APPEAR (Must be option to active back by admin if the record deleted) | Repeated (Already mentioned)
2 | Customer | Customer | Missing logic | Sales person doent view (eg. Nora) but In customer form appear. Please verify. (Salesperson,refered by,priority,payment terms,location,industry) | Repeated (Already mentioned)
3 | Admin | Random Number | Bugs | Set format in random no. "BSO-15-004012" but salesorder no. "BSO-05-00004013". Format not match. | Repeated (Already mentioned)
4 | Job | C and D | Bugs | Partial Delivery item not goes to c and d.Please rectify.( Its moving only at the time of complete all items) | New Error
5 | Job | C and D | Bugs | "Assigned To"- Appearing duplicate (eg. Arman) | Repeated (Already mentioned)
6 | Job | Invoice | Missing | Still not editable price related fields. | Repeated (Already mentioned)
7 | Customer | Costing Approval | Missing | Done good but need editable for cost when approve.(if wrong cost thn no point without edit cost) | -
8 | Job | Proforma Invoice | Missing | There is no gst,additional charge and it must be with all price related fields with editable. | New
9 | Job | Sub-Con | - | Gridview - Please display serial no. (Bcoz couldn’t identify items) | New
10 | Job | Purchase Requisition | Missing | Title (fields) not proper. It must be like quotation,salesorder. | Repeated (Already mentioned)
11 | Job | Purchase Requisition | Bugs | Instruments can insert but after save there is no records. Plz chk. | New Error
12 | Job | Purchase Order | Bugs | When save it goes to error page | Repeated (Already mentioned)
13 | Job | Onsite Schedule | Missing | After save there is no option to view record and claender has empty.plz chk | Repeated (Already mentioned)
14

## 06 JAN 15 (2)
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | USER | MISSING | CURRENCY | AFTER ADD IN AND DELETE, UNABLE TO ADD IN AGAIN. WILL INFORM ALREADY EXISTS BUT DIDN’T APPEAR
2 | CUSTOMER | MISSING | INDUSTRY | AFTER ADD IN AND DELETE, UNABLE TO ADD IN AGAIN. WILL INFORM ALREADY EXISTS BUT DIDN’T APPEAR
3 | CUSTOMER | MISSING | LOCATION | AFTER ADD IN AND DELETE, UNABLE TO ADD IN AGAIN. WILL INFORM ALREADY EXISTS BUT DIDN’T APPEAR
4 | CUSTOMER | MISSING | PAYMENT TERMS | AFTER ADD IN AND DELETE, UNABLE TO ADD IN AGAIN. WILL INFORM ALREADY EXISTS BUT DIDN’T APPEAR
5 | CUSTOMER | MISSING | PRIORITY | AFTER ADD IN AND DELETE, UNABLE TO ADD IN AGAIN. WILL INFORM ALREADY EXISTS BUT DIDN’T APPEAR
6 | CUSTOMER | CUSTOMER | ACTIVE / IN ACTIVE | DIDN’T REFLECT IN THE SYSTEM
7 | JOBS | DELIVERY ORDER | REPORT | DELIVERY ORDER NO SHOWS QUOTATION NO INSTEAD
8 | JOBS | DELIVERY ORDER | REPORT | DIDN’T SHOW REMARKS FROM THE LAB PROCESSING
9 | JOBS | C&D | COLLECTION | CANNOT ADD IN COLLECTION
10 | JOBS | C&D | COLLECTION | CANNOT PRINT PREVIEW
11 | JOBS | SUB-CON D.O | ADD SUB-CON | CANNOT EDIT AND SELECT THE ITEM
12 | JOBS | SUB-CON D.O | ADD SUB-CON | S.N NO. NOT IN ORDER
13 | JOBS | SUB-CON D.O | SAVE | An Internal Error Has Occurred.
14 | JOBS | SUB-CON D.O | ADD SUB-CON | CANNOT PRINT PREVIEW
15 | JOBS | SALES ORDER | REPORT | CANNOT VIEW THE LAST S.O NO. OF REPORT
16 | JOBS | Proforma Invoice | EDIT | S.N NO. NOT IN ORDER
17 | JOBS | Proforma Invoice | EDIT | CANNOT EDIT AND SELECT THE ITEM
18 | JOBS | Proforma Invoice | EDIT | DUPLICATE FOR THE SAME SALES ORDER
19 | JOBS | Proforma Invoice | REPORT | PRINT PREVIEW SHOWS WRONG DETAILS EXCEPT CORRECT INSTRUMENT NAME
20 | JOBS | PURCHASE REQUISITION | EDIT | CLICK ON S/N. ALL GONE
21 | JOBS | PURCHASE REQUISITION | PR-SUPERVISOR | APPROVAL DIDN’T SHOWS DETAILS
22 | JOBS | PURCHASE REQUISITION | REPORT | CANNOT PRINT PREVIEW
23 | JOBS | PURCHASE ORDER | REPORT | CANNOT PRINT PREVIEW

## 06 JAN 15
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | TYPE OF CORRECTIONS | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | Admin | Currency | Error | Double entry. When add new record it insert double.
2 | Admin | Range | missing | To Range is not compulsory. Last time ok but now not correct.
3 | Admin | salesperson | Error | please chk that I couldnt add "Nora" (prompt duplicate) but not in grid view.
4 | Admin | Priority & Payment term | Error | please chk that I couldnt add "Normal" (prompt duplicate) but not in grid view.
5 | Job | Quotation | missing | In Random - Set With start no "BQS-05-004001" but display in quote "BQS-05-4001". It must be same as Rnadom Format what we set.
6 | Job | Quotation | Error | Appear many duplication in (Additional Charge & Service Type)
7 | Job | Invoice | missing | Must editable gst,aditional charge
8
9
10
11
12
13
14

## 31 DEC 14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | TYPE OF CORRECTIONS | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | Admin-User | Error | Roles | Duplicate created when update any record.Refer Screenshot |  |  |  | Deleted Already
2 | Admin-User | Error | Department | Got Error when update. |  |  |  | Demo Link:
3 | [7 empty] | http://sam-sys.in/staging/arun/bs/
4
5
6
7
8
9
10
11
12
13
14

## 22 DEC 14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | TYPE OF CORRECTIONS | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | User | Error | User and Roles | Roles doest has operation but displaying in user screen (field-role) |  |  |  | Deleted Already
2 | User | Error | Role | I notice duplicate in roles. (operation display two times then I deleted)
3 | Customer | Missing | Customer-Tag | Technical Requirements field is missing.
4 | Customer | Missing | Costing | Missing for cost update screen. As requested normal user cannot enter cost value. User once entered instruments details in price table it should goes to dashboard for cost update and approve.
5 | Job-Quotation | Error | Instrument Price | Price not appear when do quotation. Plz chk
6 | Job-Delivery Order | Missing | Dashboard | Must Indicate in dashboard if PO need for DO. (Partial DO- Process)
7 | Job | Missing | Lab Process | RESON OF CAL "STATUS" NEED TO BE DISPLAY AS JOB MONITORING
8 | Job | Missing | Invoice | Plz include all price related fields in invoice screen from quote. Example GST, Additional Charge (Editable)
9 | job | Missing | c and d | collection cannot add. Not working.
10
11
12
13
14

## 04 DEC 14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | TYPE OF CORRECTIONS | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | JOB | ERROR | QUOTATION | WHEN UPDATE UNIT DISCOUNT ITS GETTING ERROR WITH NULL VALUE INSTEAD OF ACTUAL GIVEN VALUE.
2 | JOB | ERROR | SALES ORDER | MISMATCH INSTRUMENTS AND SERIAL NO. NOT CORRECT AS ATTACHEMNT
3 | JOB | ERROR | LAB PROCESS | MISMATCH INSTRUMENTS. TOTALLY CORRUPTED AS ATTACHMENT
4 | JOB | ERROR | DELIVERY ORDER | MISMATCH INSTRUMENTS FROM LAB PROCESS AS ATTACHEMENT
5 | JOB | ERROR | DASHBOARD-INVOICE | AFTER DO APPROVAL THERE IS NO NOTIFICATION AT DASHBOARD
6 | JOB | PENDING | OVERALL - REPORTS | NOT DONE YET.
7 | JOB | MISSING | INVOICE | PRINT ICON. MISSING
8 | JOB | PENDING | C AND D | NOT COMPLETE YET.
9
10
11
12
13
14

## 26 NOV 14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | TYPE OF CORRECTIONS | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | Admin | ERROR | Range | "Range To" field is not compulsory. (Eg. If Valus of "Range from" is 500,"Range to" is blank and "unit" is V => it should be (500)/V)
2 | Customer | SUGGESTION | Instrument Price | Button "Back to Customer" - Rename as "Save" or "Submit"
3 | Job | ERROR | Sales Order | SalesOrder from Quote - if delete instruments in salesorder it is deleting at the time but when aprove it has undeleted records.Please check.
4 | Lab Process | MISSING | Lab Process | RESON OF CAL "STATUS" NEED TO BE DISPLAY
5
6
7
8
9
10
11
12
13
14

## 19 NOV 14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | JOB | SALESORDER | INSTRUMENTS - WHEN WE REMOVE SOME INSTRUMENTS AFTER ADDED ITS WORKING FINE BUT IN APPROVAL FORM REFLECT AGAIN THAT REMOVED ITEMS.
2
3
4
5
6
7
8
9
10
11
12
13
14

## 17 NOV 14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | Admin | Overall | When do approve, It should updatable by supervisor. (Ex. Range,Unit and etc) as existing delta system.
2 | Customer | Customer | Address not saved when create new client.Please check..(Find Attached Screen Shot)
3 | Job | Sales Order | Upload not working
4 | Job | Labprocess | Processing cheked automatic instead of engineers chk and update..
5 | Job | Dashboard | Job appoval - count not working (0) when invoice count 1
6 | Job | Dashboard | Invoice Approval goes to Client PO Form instead of link to invoice approval form.
7 | Job | Invoice | Error in approval. Already Client PO Entered but its prompt for PO and couldn’t approve invoice.(Find Attached Screen Shot)
8 | Job | Sales Order | After sales order (Without Quotation BSQ) completed, It should assigned in quotation dashboard and once approved then it goes to sales order dashboard for approval. But currently display in both.
9 | Job | Sales Order | Error in Email value populate in text box when create new sales order
10 | Job | Delivery Order | Error in Attn value populate in text box when create partial delivery order
11 | Job | Delivery Order | Error in Partial Delivery Order.(Find Attached Screen Shot)
12
13
14

## 05 NOV 14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | JOB | SALES ORDER | I CAN REMOVE INSTRUMENTS NOW WHEN I DO SALES ORDER FROM QUOTATION BUT WHEN I APPROVE IT SHOWS ALL INSTRUMENTS AGAIN.PLEASE CHECK
2 | JOB | LAB PROCESS | DASHBOARD -JOB STATUS SHOWS WRONGLY.PLEASE CHECK SCREENSHOT.
3 | JOB | LAB PROCESS | ERROR WHEN UPDATE STATUS AS ATTACHEMENT
4 | JOB | DELIVERY ORDER | COULDN’T APPROVE. PROBLEM
5 | JOB
6
7
8
9
10
11
12
13
14

## 28 OCT 14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | User | Branch | Phone No- 8 char only..please remove 9 char.
2 | User | Currancy | Allow 5 char bcoz some countries doent have symbol we must enter code there.
3 | Customer | Customer | Missing Technical requirements field.( As discussed already)
4 | Customer | Customer | Instrument price list - it doesnt allow same model no to different customer. If same customer it must block duplicate but different customer must allow for model and range.
5 | Instrument | Instrument | It shouldn’t be allow duplicate even when enter caps or small letter combination.
6 | Job | Quotation | Instruments grid view - It must display all fields like range,brand and all but in report, as we discussed with limited fields.
7 | Overall | Approval | Must be editable all fields at the time of approval because main purpose of approve to correct the mistakes before do approval.
8 | Job | Sales Order | Sales order from Quotation - It should be allow to add or delete option for instruments. (Like existing delta software)
9 | Dashboard | Delivery Order | Please display DO Number to identify for easy approval
10 | Job | Delivery Order | Its not working properly.
11
12
13
14

## 22-Sep-14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | Instrument | Instrument | Increase size for length..refer existing delta
2 | Job | Quote And Salesorder | When select instrument, Binding values - Very slow (Plz Check)
3 | Job | Quote And Salesorder | Additional Fields (Tittle) - Please add same as our existing delta
4 | Job | Quote And Salesorder | Instruments Dtails Grid View - Please do as our existing Delta. Current Your System display few fields only but want to view all values for our references.
5 | Job | Salesorder | When prepare salesorder from existing quote, in instruments details-System must allow to 1.Add new instruments details 2.Delete instruments details and 3.edit instruments details too. If any changes do in salesorder,it must approve by sales team and also reflect in quote automatically.
6 | Job | Salesorder | When prepare salesorder from existing quote, User can change priority.Plz allow.
7 | Job | Quote And Salesorder | Before approve salesorder (BSO),the system display quotation(BSQ) in grid list and also allowing to edit.
8 | OverAll | GridView List | It should display latest first in grid list. Sort by date. Please implement to overall.
9 | Job | Salesorder | Missing ourref no. Please follow as existing delta
10 | job | Salesorder | gridview must be existing delta. Please follow delta and don’t restrict view field with less items.
11 | Job | Salesorder | When prepare salesorder from existing quote, service type value is not same as quote.
12 | Customer | Customer | when do update,Plz prompt "Succesfully Saved". Otherwise user get confuse. Implete overall for add,edit or delete and approved.
13 | Job | Salesorder | Cannot save when prepare withot quote. Error. Plz check
14 | Job | Labprocess | Error as attachement.Plz chk
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## 10-Sep-14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | User | Roles | Duplicated SuperAdmin. Please Check
2 | User | Currency | Duplicated Singapore Dollar. Please Check
3 | Customer | Priority | When try to add duplicate, it should prompt already exist. Its not allow and working fine but also need prompt msg.
4 | Overall | - | Please prompt if already exist when add duplicate records.
5 | Job | Quote & SalesOrder | Missing option to generate PONO as in quotation. As discussed it should be in SO also.
6 | Job | Quote & SalesOrder | Priority - DueDate. When change priority must change Duedate also automaticaly.
7 | Job | Quote & SalesOrder | Instrument not user friendly when select from combobox. Some instruments not appear its something wrong.
8 | Job | Quote & SalesOrder | Model no. not searchable.How to select diff model no after select instrument. Please follow as existing delta
9 | job | Quote & SalesOrder | Its allowing to add without select values range,model no and all. Its wrong. Please follow as existing delta
10 | Customer | InstrumentPrice | Range not included unit. It should be range and unit togather.Please follow existing delta.
11 | Job | SalesOrder | Option to filter customer wise when import the quotation details..Please follow our existing delta.
12 | Job | Quote & SalesOrder | please make differentiate bw bsq n bqs
13
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## 01-Sept-14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | User | Roles | Incomplete. Only user module done. | 2014-08-01
2 | User | Currency | Error-Not Saved. There is no record when I add new "S$" singapore currency | 2014-08-01
3 | Customer | Payment Terms | Error. There is no record when I add new "30 Days" | 2014-08-01
4 | All Modules | Search | Please add search feature for each module and submodule (eg.customer,instruments,paymentterms and all). Its not new feature. Its included already in our existing delta. | 2014-08-01
5 | Customer | Customer | Need Technical special requirements filed. Please add. Existing system included this. | 2014-08-01
6 | Customer | Customer | Without approval, it shouldn’t be allow to use in quote or salesorder. But now allowing.its wrong. | 2014-08-01
7 | Customer | Customer | Contact - There is no option to edit contact. Delete option only there. | 2014-08-01
8 | All Modules | Approval | Without approval, it shouldn’t be allow to use. But now allowing.its wrong. (eg. Customer,Brand,range and all) | 2014-08-01
9 | Instruments | Brand | Need approval for each new entry. Please add in dashboard for approval. | 2014-08-01
10 | Instruments | Filter | Option to display for particular related range/brand/unit values of each instruments. Expample Like our existing system. | 2014-08-01
11 | Instruments | ProcedureNo | No Records. Its not working. Please check. | 2014-08-01
12
13
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## 20-Aug-14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | Dashboard | Client PO | Tag message wrong. It should be "No client Po records" like ths not C & D | 2014-08-20
2 | Dashboard | Customer | Must need to approval option | 2014-08-20
3 | Dashboard | Range | No Approval button | 2014-08-20
4 | Dashboard | Quotation | Not Quote Nos displayed. It should quote no included when approve. | 2014-08-20
5 | Admin-User | Branch | When add branch,it prompt already exist but nothing added in same name. | 2014-08-20
6 | Admin-User | Branch | Got error | 2014-08-20
7 | Admin-Customer | Customer | Delivery address not working. It combined if add more than one. | 2014-08-20
8 | Admin-Customer | Customer | Phone & Fax must. Compulsory field | 2014-08-20
9 | Admin-Customer | Customer | First tab remove submit button. It should be in last tab. | 2014-08-20
10 | Admin-Customer | Contact | Name & Email must.Compulsory field. But its allowing now. | 2014-08-20
11 | Admin-User | Priority | Must allow to multifly 1.5 (decimal) | 2014-08-20
12 | Admin-Instr | Instrument | Follow same us existing software. You not filtered all fields by dept. it shows all dept datas in range,unit and all. Its wrong. | 2014-08-20
13 | Admin-Instr | Range & Unit | Both not working. After saved it shows inactive. Even corrected when approve its remain inactive. After save,it remain same page. | 2014-08-20
14 | Dashboard | Procedure | Display Error | 2014-08-20
15 | Dashboard | Instrument | Display Error | 2014-08-20
16 | Admin-Customer | Customer Instr Price | Its not working. No units with range. Price updates wrongly what entered.When edit,it display null. | 2014-08-20
17 | Job | Quotation | Cal type not call type. Cal type should be autofill. | 2014-08-20
18 | Job | Upload File | Its not working. Got Error. | 2014-08-20
19 | Job | Sales Order | Instr description - dublicate 2 times. Range box has "select brand" wrongly. | 2014-08-20
20 | Job | Delivery Order | Allow duplicate. It display 2 times what entered. | 2014-08-20
21 | Job | C and D | Cannot add. Got error. Also cannot move delivery item to DO list.Got error. | 2014-08-20
22 | Job | Tittle field | Nothing there. Not working. | 2014-08-20
23 | Reset Button | - | overall not neccessory | 2014-08-20
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## 14-Aug-14
BS ENTERPRISE - CORRECTIONS & REQUIREMENTS
No. | Module | Sub-Module | Problem & Explanation | Assigned Date | Completed Date | Status | Remarks
1 | Dashboard | Home Description | Move to login page. Only keep Approval and message tab in dashboard. | 2014-08-13
2 | Dashboard | View & Priority | First Approval-Second Sales Chart - Calender | 2014-08-13
3 | Dashboard | All | Funionaly not working but template is ok. | 2014-08-13
4 | Admin-User | Role | After submit need display "Saved Successfully". Now It remains same page so we cannot understand wheather saved or not. | 2014-08-13
5 | Admin-User | Role | Completed for permission but for others are pending | 2014-08-13
6 | Customer | Customer | without contact entry,it allow to save now but it should be prompt and not allow. | 2014-08-14
7 | Customer | Customer-Tag | It is not working. When add new,we cannot save & got error. | 2014-08-14
8 | Customer | Customer-Tag | Tag List - Goes to error page when click | 2014-08-14
9 | Customer | Customer-Tag | There is no option for PO Ack Type selection in tag but customer form appear. | 2014-08-14
10 | Customer | Customer & Tag | Missing special requirements of technical (please check bsdelta) | 2014-08-14
11 | Instrument | Instrument | After done instrument,I cannot go other page. I cannot navigate customer or other menu. | 2014-08-14
12 | Instrument | Instrument Price | Range cannot select | 2014-08-14
13 | Instrument | Instrument price | As requested, havent done advansed search feature for instrument price form fields | 2014-08-14
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-